## todo's
LOX , ELECTOLYSER, FUEL CELL AND LIQUID LIQUD EXTRACTION
Action&Decision List 17/03/22
Section | TODO Item | Responsible | Status (open/in work/done) | Notes
electrolyser | installation of the 2 pumps | SAMER | done
electrolyser | تركيب الrubber لمنع التسريب | SAMER | done
electrolyser | تصليح موقع الVALVES | SAMER | done
lox | INSTALLATION OF THE COMPRESSOR | WORKER | done
FUEL CELL | Design of the bipolar | Mariam | done
FUEL CELL | Freecad Design of Gasket | Mariam | done
FUEL CELL | looking how many the designed bipolar costs | Noor | done
elektrolyser | testing the pump system if the pressure is too high | Abdullah and Raja | done | 1
elektrolyser | installation of the remaining parts | Samer | done | 2
elektrolyser | cutting the level control bars to the wanted level | Abdullah | done | x
elektrolyser | adding a level control software to the level control system | Abu Omar |  | 3
4
elektrolyser | adding the current to the plant | othman and Abu Omar / Abu Omar |  | 5
elektrolyser | ("1/2) buying electric valves | Noor or Abdullah | done | 5
elektrolyser | exchange the valves with electric valves | samer | done | 6
elektrolyser | making a more realistic flow chart | Abu Omar |  | last-2
elektrolyser | (with th flow chart made by a trainee ) some changes in the Gui | Abu Omar |  | last-1
elektrolyser | testing the whole system without the current for the electrolysis | Abdullah and Raja and Abu Omar |  | last
electrolyser | testing the wholr systeme with the current | the whole team
ashes recycling | reconstruct the pipe system | Samer | done
ashes recycling | updaiting the wanted parts and install them | Abu Omar |  | 1
ashes recycling | PROCESS CONTROL SYSTEM | Abu Omar |  | 2
ashes recycling | GUI | Abu Omar |  | 3
ashes recycling | testing the ashes recyclicling process control system with water | Abdullah and Abu Omar |  | 4
ashes recycling | testing with colored water and oil | Abdullah and Abu Omar |  | 5
ashes recycling | deliver the chemicals needed for the extraction | Abdullah |  | 6
ashes recycling | testing with the chemicals | Abdullah and Abu Omar |  | 7

## contacts
name | role | number | worket at | what he did
Nasser Krayem (Nours brother) | schredder supplier | 76911737 | NLAP-IPP
Mahmoud Abou Mustafa Abou Watan (compres- sor) | معلم compressor | 71982493 | LOX
Maher Dib (compressor) | معلم compressor | 70414767 | LOX
Fadi chehade (خال Jana Ghemrawi) | conveyer suppplier | 3186587 | NLAP-IPP
Samer Youssef | PPR Master | 79171593 | AECENAR
Osman Dhaybe | mechanical master | 81105029 | AECENAR

## finances
finances
LOX | [6 empty] | elecrolyser |  |  |  |  | Liquid Liquid Extraction |  | MEGBI
| man $ |  |  | material $ |  |  | man $ |  |  | material $ |  |  |  | man $ |  | material $
2021-11-12 | 39,0 (800 000) | compressor worker دفعة أولى | 2021-11-12 | 350 | compressor | samer | 94 | ppr installation | 2021-11-12 | 40 | water pump |  | 2021-11-24 | 13 | second payment for the lab refrigerator
[6 empty] | osman | 22.6 | ppr installation | 2021-11-12 | 45 | ppr
[6 empty] | samer | 9 | ppr installation | 2021-11-22 | 51 | ppr
[9 empty] | 2021-11-22 | 20 | silicon
[9 empty] | 2021-11-22 | 10 | rubber
[9 empty] | 2021-11-28 | 25 | ppr