## January to April 2022
Priority
MEGBI-APP TODOs/Responsibilities
Action&Decision List 17/2/2022
open Tasks
Section | TODO Item | Remarks | Responsible | Due Date | Status (open/in work/done) | Notes
steam cycle | استبدال الcondenser manual valve لوجود تسريبات |  | Jihad and Ahmad |  | done | Priority
steam cycle | اعادة تعديل اتجاه انبوب التفريغ الخارجي الى الاعلى عوضا عن الاتجاه الجانبي بشكل مناسب |  | Jihad and Ahmad |  | done | Priority
Steam Cycle | تغيير الpressure gauges عدد 2 |  | Jihad and Ahmad |  | done | Priority
steam cycle | فحص الmechanical safty valve يدويا عبر مكنة ضغط |  | Jihad and Ahmad |  | done
steam cycle/control | فحص الcondenser discharge valve (controlled by GUI) قد تكون مبرمجة لتفتح على 14 Bar |  | Rajaa |  | done | Priority
cooling cycle | تقوية نظام التبريد عبر اضافة pump |  |  |  | canceled
steam cycle | تشغيل الpump الصغيرة التي تسحب البخار من الcondenser لخزان التفريغ |  | jihad and Nour/Raja |  | done
steam cycle | معالجة تسريبات انابيب البخار المتجهة الى غرفة التفريغ |  | Jihad and Ahmad |  | done
steam cycle | معالجة تسريبات البخار من تحت التربين |  | Jihad and Ahmad |  | done
Documentation | Citation of the updated report |  | Hind | 2022-04-01 | done | Priority
| Printing of annual report +poster | 60.000 L.L | Hind | 2022-04-01 | done | Priority
Penicillin quantification | Penicillin G bringing |  | Nour Krayem | 2022-04-01 | done
| BaCl2 weight |  | Hind | 2022-04-01 | done | Priority
| Autoclave |  | Hind/Nour |  | done | Priority
| Make a consevetative bacterium in glycerol |  | Hind |  | open | to avoid strains lost
| E.coli and Streptococcus strains from Ecole doctorale |  | Hind | From 3 to 10/1/2022 | done | Priority
| Get a permission from Chamber of commerce | Dr. Khaled el omari (incubateur) | Hind |  | open
| Antibiotic sensitivity disks |  | Hind/Nour/Abdallah | after penicillin recruitement | done
Pilot plant penicillin production | Ethyl acetate production |  | Hind |  | cancelled
steam cycle/control | تعديل ارقام الضغط على الGUI (/100) |  |  |  | canceled
incineration cycle | زيادة الO2 للحرق عبر تركيب مراوح على supply fans البوابة الجانبية |  | Jihad and Ahmad |  | done | priority
incineration cycle | تنظيف المحرقة من الداخل و الخارج |  | Worker x |  | done | Priority
| Distillation set from Mr. Burhan Kabbara |  | Hind | Wednesday 23/2/2022 | done
| whole study to turn on the bioreactor |  | Hind |  | done
| Centrıfuge |  | Hınd |  | open
| TPY agar preparation |  | Hind | After Autoclave bringing | cancelled | it is not important because we have a medium culture
| Milk recruitement |  | Hind |  | open
| Petri dishes |  | Nour Krayem |  | done
Ampicillin production | Enzyme recruiting | By calling Numelab with an e-mails | Hind |  | done
| Enzyme recruiting from another source | ddu/ sigma aldrich or pmc biochem | Hind |  | done | Priority
incineration cycle | تغطية المروحة الجانبية من مياه الأمطار |  | Ahmad |  | done | Priority
Ampicillin Quantification | Assure if presented ampicillin work well or not | After E.coli bringing | Hind | From 3 to 10/1/2022 | done
| make the antibiotic standard solution | in zotero | Hind |  | open | Priority
filtration cycle | تشغيل الearthening |  | Rajaa , abdalla, Hamad | 2022-12-25 | done
filtration cycle | إستبدال الكابلات الموصولة على الإلكترو فلتر بكابل 10mm |  | Rajaa, abdalla,Ali | 2022-12-25 | done | Priority
filtration cycle | فحص و تغيير مكان المروحة المركبة اول الexhaust |  | Jihad and Ahmad |  | done | Priority
filtration cycle | تركيب earting للإلكترو فلتر |  | Rajaa, abdalla, Hamad | 2022-12-25 | done | Priority
Aspirine production | Poster |  | Ihab | From 3 to 10/1/2022 | open | Priority
| Materials bringing | Only the acetic anhydride remain | Nour Krayem |  | open
steam cycle | تركيب temperature gauge(big size) |  | Jihad and Ahmad |  | done | Priority
Turbine | تجهيز التربين احضار معلم |  |  |  | canceled
Turbine | تشغيل Turbine expension valve |  | Rajaa |  | done
cooling cycle | تلحيم خط التبريد بارضية المحطة للتثبيت |  | ahmad |  | done | Priority
cooling cycle | نقل أنابيب التبريد من على منصة المحطة لأسفلها (من أجل تركيب الجارور) |  |  |  | canceled
incineration cycle | تغليف او عزل المحرقة
steam cycle | قلب اتجاه الcondenser expension valve |  | Jihad and ahmad |  | done
- | تلحيم درج لغرفة التربين |  | ahmad |  | done
controle | فحص كابل الsensor |  | hamad |  | done
Seurity | تركيب ممشى حول المحرقة |  | Mhammad kammah
Seurity | تركيب كاميرات للمراقبة
Seurity | تركيب earth لل x-ray

## May 2022
Sect+B3:H24ion | TODO(s) Item | Remarks | Responsible(s) | Due Date | Status (open/in work/done) | Notes
Penicillin | penicillium cultivation in tryptone agar | incubation for 4 days | Hind | 16/5/2022 | done
| Penicillium cultivation in liquid medium | incubation for 1 week | Hind | 20/5/2022 | open
Ampicillin | E.coli and staph aureus culture | incubation for 24 hours | Hind | 16/5/2022 | done
| Making Antibiotic standard solution |  | Hind | 17/5/2022 | open
| Making muller hinton agar+ autoclavage |  | Hind | 17/5/2022
Documentation | Whole study of requirements for large scale |  |  |  | open
Pilot plant production