(((

Institute for Strategic Studies and International Relations (ISSIR)

Planning Jan – Jun 2012

Initial Document: 9 Jan 2012

Last update: 10.01.2012

Content

1	Institute	2

1.1	Goal of ISSIR	2

1.2	Scientific Areas	2

2	ISSIR Structure	3

3	Achieved Working Packages and Costs 2011	4

3.1	Achieved Working Packages with the help of Allah	4

3.2	Ressources (Human Ressources, Time, Costs)	4

3.2.1	Human Ressources	4

3.2.2	Time	4

3.2.3	Costs	4

4	Planned Working Packages and Costs 2012	5

4.1	Planned Working Packages according to departments	5

4.1.1	EUSH - European Social System and History	5

4.1.2	FPME – Neighbour and Foreign Policy Concepts for Middle East Countries	5

4.1.3	TPME - Technology Policy Concepts for Middle East Countries	6

4.1.4	ISSIR commonly	6

4.2	Ressources (Human Ressources, Time, Costs)	6

4.2.1	Human Ressources	6

4.2.2	Time	6

4.2.3	Costs	6

# Institute

## Goal of ISSIR

ISSIR undertakes analysis in different fields and gives advices to decision makers in policy and economy – especially in the new countries in the Middle East region.

## Scientific Areas

International Politics, International Law, Economy and State Law in Middle East Countries to be Compatible to Islamic Rule, International Economy, New and Contemporary History

# ISSIR Structure

ISSIR Structure

# Achieved Working Packages and Costs 2011

## Achieved Working Packages with the help of Allah

Initiation of ISSIR

Weekly Seminary (about 4 times)

ISSIR Journal 1st Ed. (arabic Ed. printed (1000 copies for 700 EUR), English Ed. as OnlineJournal), with 3 parts for the three reseach topics “Concepts for Middle East Countries”, „Western – Islamic World Relationships“ and „Behaviour Patterns in international politics”

## Ressources (Human Ressources, Time, Costs)

### Human Ressources

1 Project leader (1,5 man months (MM))

7 persons (0,5 MM each)

-> 5 MM

### Time

February – June

-> 5 months

### Costs

# Planned Working Packages and Costs 2012

## Planned Working Packages according to departments

In the following the working packages are listed. The result of every working package has to be published as an article in the ISSIR Journal, 2nd edition (June 2012).

### EUSH - European Social System and History

A working package will be worked out insha Allah in the following period (Jul – Dec 2012) (Bilal)

### FPME – Neighbour and Foreign Policy Concepts for Middle East Countries

#### Analysis of Middle East Social Systems and Inner Conflict Potentials:

History of Iran and Iranian Social System (Social and Religious Groups, Political System, particular Shia topics concerning the relation to Sunna)

Contemporary History of Turkey (1850 – 2000) and Turkish Social System (Social and Religious Groups)

Contemporary History of Egypt (1850 – 2000) and Egypt Social System (Social and Religious Groups)

This analysis aims to estimate the possibility of a major Sunni - Shia Clash and shall give possibilities to avoid this.

(Roula)

#### Deeper Analysis of Relationship between Islamic Countries and Imperial American Power

-> Analysis of American problems and their policy towards Islamic countries according to “Emanuell Todd, USA-Ein Nachruf” (Mariam) (about 5 pages article)

#### The strategical options for Islamic Sunni Countries

Seeking a strategical pact with Shia countries to make one front against American aggression (Turkey-Egypt-Syria-Iran-Irak against USA)

Seeking a pact with Western Countries against Shia „bad“ brother countries (Turkey-Egypt-Western Countries against Iran)

Learning from success of Salahuddin

Salahuddin was good and tolerant to Shia population in Egypt and so it was possible to unite Egypt and Syria one hand to concentrate the energy against the crusaders.

Learning from Bismarcks policy and Wilhelm II. mistakes

To isolate the real / number one enemy it is necessary to have good relations to all other actors.

Bismarck had seeked good relationship to all European countries to isolate France after 1871.

### TPME - Technology Policy Concepts for Middle East Countries

Analysis:

Survey about the companies in key technology sectors (Food, Water,…) in Bilad ash-Sham Countries (Syria, Lebanon, Jordan): List of Suppliers (both producers and distributors)

(Samir, Mohammad Ridouan Hejazi)

### ISSIR commonly

Establishing the ISSIR library. The next step is a ISSIR bureau in Tripoli (Jul – Dec 2012).

## Ressources (Human Ressources, Time, Costs)

### Human Ressources

1 project leader (1 man month)

4 voluntary persons (0,5 man month each)

### Time

6 months

### Costs

1200 EUR for printing 2nd (600 EUR for Arabic edition, 600 EUR for English edition)

# Text boxes

Research

Research

Education

ISSIR

Publishing

Bachelor Programs

International Relations

Political Sciences

ISSIR Magazine planned to appear every 6 months

FPME - Foreign Policy Concepts for Middle East Countries

TPME - Technology Policy Concepts for Middle East Countries

EUSH - European Social System and History